## Sheet1
[7 empty] | 2024-07-08 |  |  |  |  | 2024-08-12 |  |  |  | 2024-09-09 |  |  |  |  | 2024-10-14 |  |  |  | 2024-11-11 |  |  |  | 2024-12-09
| 2024-07-29 | Semester Start Date 15th July 2024 |  |  |  | Week |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
|  |  | Subject | Sem 2 Dual Diploma |  |  |  | 2024-07-01 | 2024-07-08 | 2024-07-15 | 2024-07-22 | 2024-07-29 | 2024-08-05 | 2024-08-12 | 2024-08-19 | 2024-08-26 | 2024-09-02 | 2024-09-09 | 2024-09-16 | 2024-09-23 | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23 | 2024-12-30
Activity | Start | End | Days | Status | % Done | Subject
NO LAP | 2024-07-15 | 2024-07-15 | 1 | Not Started | 5% | Web App Development (NO LAP) | bar: 2024-07-08
AT1 Portfolio | 2024-07-15 | 2024-07-22 | 6 | Overdue | 5% | Information Architecture | bar: 2024-07-15
Journal Wk1 | 2024-07-15 | 2024-07-22 | 6 | Overdue | 5% | SaaS (NO LAP) | bar: 2024-07-15
Research Wk1 | 2024-07-15 | 2024-07-22 | 6 | Overdue | 5% | SaaS (NO LAP) | bar: 2024-07-15
Journal Wk2 | 2024-07-22 | 2024-07-29 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-07-22
Research Wk2 | 2024-07-22 | 2024-07-29 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-07-22
AT2 Pt.1 - Requirements Summary | 2024-07-15 | 2024-08-05 | 16 | Not Started | 5% | Information Architecture | bar: 2024-07-29
Journal Wk3 | 2024-07-29 | 2024-08-05 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-07-29
Research Wk3 | 2024-07-29 | 2024-08-05 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-07-29
AT7 (PartA) - KBA | 2024-07-15 | 2024-08-12 | 21 | Not Started | 5% | Data and Machine Learning | bar: 2024-08-05
Journal Wk4 | 2024-08-05 | 2024-08-12 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-08-05
Presentation - AT1 | 2024-07-29 | 2024-08-12 | 11 | Not Started | 5% | Data and Machine Learning | bar: 2024-08-05
Research Wk4 | 2024-08-05 | 2024-08-12 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-08-05
AT1 - KBA | 2024-08-12 | 2024-08-19 | 6 | Not Started | 5% | Cyber Awareness | bar: 2024-08-12
AT2 Pt.2 – Design Report | 2024-07-15 | 2024-08-19 | 26 | Not Started | 5% | Information Architecture | bar: 2024-08-12
Journal Wk5 | 2024-08-12 | 2024-08-19 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-08-12
Research Wk5 | 2024-08-12 | 2024-08-19 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-08-12
AT2 Pt.3 - Mockup | 2024-07-15 | 2024-08-26 | 31 | Not Started | 5% | Information Architecture | bar: 2024-08-19
Journal Wk6 | 2024-08-19 | 2024-08-26 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-08-19
KBA | 2024-08-12 | 2024-08-26 | 11 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-08-19
Research Wk6 | 2024-08-19 | 2024-08-26 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-08-19
Activity 1 | 2024-07-15 | 2024-09-02 | 36 | Not Started | 5% | Cyber Awareness | bar: 2024-08-26
Activity 2 (Part 1) | 2024-07-22 | 2024-09-02 | 31 | Not Started | 5% | Cyber Awareness | bar: 2024-08-26
Activity 2 (Part 2) | 2024-07-29 | 2024-09-02 | 26 | Not Started | 5% | Cyber Awareness | bar: 2024-08-26
Activity 3 | 2024-08-19 | 2024-09-02 | 11 | Not Started | 5% | Cyber Awareness | bar: 2024-08-26
AT1 - Portfolio | 2024-08-05 | 2024-09-02 | 21 | Not Started | 5% | Advanced Mobile Development | bar: 2024-08-26
AT2 Pt.4 - Prototype | 2024-07-15 | 2024-09-02 | 36 | Not Started | 5% | Information Architecture | bar: 2024-08-26
Journal Wk7 | 2024-08-26 | 2024-09-02 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-08-26
Presentation - Portfolio | 2024-08-12 | 2024-09-02 | 16 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-08-26
Research Wk7 | 2024-08-26 | 2024-09-02 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-08-26
AT2 Pt.5 – Prototype Test | 2024-07-15 | 2024-09-09 | 41 | Not Started | 5% | Information Architecture | bar: 2024-09-02
Journal Wk8 | 2024-09-02 | 2024-09-09 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-09-02
Presentation - Performance Assessment | 2024-08-19 | 2024-09-09 | 16 | Not Started | 5% | Cyber Awareness | bar: 2024-09-02
Research Wk8 | 2024-09-02 | 2024-09-09 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-09-02
API Liveworks Project | 2024-08-26 | 2024-09-16 | 16 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-09-09
Journal Wk9 | 2024-09-09 | 2024-09-16 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-09-09
Presentation - AT2 – Power BI | 2024-09-02 | 2024-09-16 | 11 | Not Started | 5% | Data and Machine Learning | bar: 2024-09-09
Research Wk9 | 2024-09-09 | 2024-09-16 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-09-09
Journal Wk10 | 2024-09-16 | 2024-09-23 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-09-16
Research Wk10 | 2024-09-16 | 2024-09-23 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-09-16
Journal Wk11 | 2024-09-23 | 2024-09-30 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-09-23
Research Wk11 | 2024-09-23 | 2024-09-30 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-09-23
AT2 (A) – Documentation (Part 1) | 2024-09-09 | 2024-10-07 | 21 | Not Started | 5% | Advanced Mobile Development | bar: 2024-09-30
Journal Wk12 | 2024-09-30 | 2024-10-07 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-09-30
Research Wk12 | 2024-09-30 | 2024-10-07 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-09-30
Journal Wk13 | 2024-10-07 | 2024-10-14 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-10-07
Research Wk13 | 2024-10-07 | 2024-10-14 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-10-07
Journal Wk14 | 2024-10-14 | 2024-10-21 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-10-14
Research Wk14 | 2024-10-14 | 2024-10-21 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-10-14
AT3 - Anagram and Palindromes | 2024-09-20 | 2024-10-28 | 27 | Not Started | 5% | Data and Machine Learning | bar: 2024-10-21
AT4 - Analysis Weather Data | 2024-10-14 | 2024-10-28 | 11 | Not Started | 5% | Data and Machine Learning | bar: 2024-10-21
AT5 - Analysis Baby Names | 2024-10-21 | 2024-10-28 | 6 | Not Started | 5% | Data and Machine Learning | bar: 2024-10-21
Journal Wk15 | 2024-10-21 | 2024-10-28 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-10-21
Research Wk15 | 2024-10-21 | 2024-10-28 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-10-21
AT1 (A) – Sprint Planning | 2024-07-15 | 2024-11-04 | 81 | Not Started | 5% | Innovation Project | bar: 2024-10-28
AT1 (B) – Sprint | 2024-07-15 | 2024-11-04 | 81 | Not Started | 5% | Innovation Project | bar: 2024-10-28
AT1 (C) – Retrospective | 2024-07-15 | 2024-11-04 | 81 | Not Started | 5% | Innovation Project | bar: 2024-10-28
Journal Wk16 | 2024-10-28 | 2024-11-04 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-10-28
Research Wk16 | 2024-10-28 | 2024-11-04 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-10-28
Journal Wk17 | 2024-11-04 | 2024-11-11 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-11-04
Research Wk17 | 2024-11-04 | 2024-11-11 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-11-04
AT2 - KBA | 2024-11-04 | 2024-11-18 | 11 | Not Started | 5% | Innovation Project | bar: 2024-11-11
AT2 – Self-Reflection | 2024-07-15 | 2024-11-18 | 91 | Not Started | 5% | Innovation Project | bar: 2024-11-11
AT2 (B) - Project | 2024-07-15 | 2024-11-18 | 91 | Not Started | 5% | Advanced Mobile Development | bar: 2024-11-11
AT6 | 2024-11-04 | 2024-11-18 | 11 | Not Started | 5% | Data and Machine Learning | bar: 2024-11-11
AT7 (Part B) - KBA | 2024-11-04 | 2024-11-18 | 11 | Not Started | 5% | Data and Machine Learning | bar: 2024-11-11
AT7 (Part C) - KBA | 2024-11-04 | 2024-11-18 | 11 | Not Started | 5% | Data and Machine Learning | bar: 2024-11-11
Journal Wk18 | 2024-11-11 | 2024-11-18 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-11-11
Research Wk18 | 2024-11-11 | 2024-11-18 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-11-11
AT3 - KBA | 2024-11-11 | 2024-11-22 | 10 | Not Started | 5% | Advanced Mobile Development | bar: 2024-11-11
Journal Wk19 | 2024-11-18 | 2024-11-25 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-11-18
Presentation - NoSQL/MongoDB Portfolio | 2024-08-12 | 2024-11-25 | 76 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-11-18
Research Wk19 | 2024-11-18 | 2024-11-25 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-11-18
Journal Wk20 | 2024-11-25 | 2024-12-02 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-11-25
Research Wk20 | 2024-11-25 | 2024-12-02 | 6 | Not Started | 5% | SaaS (NO LAP) | bar: 2024-11-25
Formulas:
Days = IF([End]="","",NETWORKDAYS([Start],[End]))
End = [Start]+7

## Lists
Status | Subject
Not Started | Information Architecture
In progress | Web App Development (NO LAP)
Overdue | Advanced Mobile Development
Complete | Cyber Awareness
Innovation Project
SaaS (NO LAP)
Data and Machine Learning